## Summary of completion
Column Labels
| Done | (blank) | Grand Total
Sum of Priority S | 998.6 | 2156.9976 | 3155.5976
31.65%
Column Labels
| Done | (blank) | Grand Total
Sum of Importance S | 81 | 287 | 368
22.01%
Column Labels
| Done | (blank) | Grand Total
Sum of Impact S | 68 | 599 | 667
10.19%

## Source lists
Sections | Features | Sub-Feature | Importance | Score | Impact |  | Complexity
Calendar/Appointments | Appointments modal | Cancelling/Voiding | Breaks App | 10 | USP | 10 | Whole new section | 10
Clients | Bank statement importer | Client Feedback Section | Does not function as expected | 8 | New feature | 7 | Whole new feature | 8
Dashboard and Main Menu | Bulk uploads | Date picker | Poor UX | 4 | Feature enhancement/fix | 6 | New component/service with complex integration | 7
Finance - Accounting | Calendar | Footer bar | Poor UI | 3 | Improved UX | 4 | New component/service with simple integration | 5
Finance - Invoicing | Client lists | Forgot password | Nice to have | 1 | Improved UI | 3 | Major change to current component | 4
Finance - Payments | Client modal | Generate invoices parms |  |  | Refactor/Tech debt | 1 | Investigation and change | 3
Finance - Reports | Dashboard | Generate invoices results |  |  |  |  | Minor change to current component | 2
General | Drop down menu | Landing Section with call to action |  |  |  |  | Minor tweak | 1
Lifestock management | Generate invoices | Log out
Marketing | Invoice list | Login error warnings
Navbar | Invoice view | Our Features Section
Staff management | Landing Page | Register
User Management | Login Button | Third party login
Booking | Logo | User details modal
Login/Register | Main menu | What's New Section
| Payment list | Your calendar drop down
| Payment modal | Register error warnings
PDF export
Report - Profit and lose
Sign in Modal
Utility services
Warnings
Report - Review by instructor
Report - Review by horse
Report - Expenses by instructor
Report - Expenses by horse
Report - Contribution by instructor
Report - Contribution by horse
Lesson booking platform
Statement runs
Profile portal
Register modal

## Issues 3-1-24
# | Section | Features | Sub-Feature | Description | Importance | Impact | Complexity | Importance S | Impact S | Priority S | Dependency # | Status
53 | Calendar/Appointments | Appointments modal | Cancelling/Voiding | If an appointment is cancelled but that have been previously invoiced - then this needs to be credit noted | Does not function as expected | USP | Major change to current component | 8 | 10 | 200 | 77 | Done
6 | Navbar | Login Button |  | Should be added to Navbar | Poor UX | New feature | Minor change to current component | 4 | 7 | 98 | 1 | Done
77 | Finance - Payments | Payment modal |  | Voiding payments does not work | Does not function as expected | Feature enhancement/fix | Investigation and change | 8 | 6 | 96 |  | Done
90 | Clients | Client modal |  | Remove client is not working | Does not function as expected | Feature enhancement/fix | Investigation and change | 8 | 6 | 96 |  | Done
112 | Finance - Reports | Statement runs |  | Statements do not show credit notes (where required) | Does not function as expected | Feature enhancement/fix | Investigation and change | 8 | 6 | 96 | 53 | Done
114 | Finance - Payments | Payment modal |  | Payment are not being recorded correctly | Does not function as expected | Feature enhancement/fix | Investigation and change | 8 | 6 | 96 |  | Done
45 | Calendar/Appointments | Calendar | Date picker | Should have a date picker at the top of the calendar | Poor UX | Feature enhancement/fix | Minor change to current component | 4 | 6 | 72 |  | Done
32 | Navbar | Logo |  | On hovering the logo the cursor should be pointer | Poor UX | Improved UX | Minor tweak | 4 | 4 | 64 |  | Done
113 | Login/Register | Register modal |  | Needs to be a modal specfically for registrations | Does not function as expected | Feature enhancement/fix | New component/service with simple integration | 8 | 6 | 57.6 |  | Done
25 | User Management | Sign in Modal |  | After trying to register (and assuming it fails) and attempts in future to sign in will result in a registration attempt | Breaks App | Improved UX | Investigation and change | 10 | 4 | 53.3333 |  | Done
59 | Finance - Invoicing | Invoice view |  | The detail should reference the instructor | Nice to have | USP | Minor change to current component | 1 | 10 | 50 | 60
60 | Calendar/Appointments | Appointments modal |  | New appointments should be able select an instructor | Nice to have | USP | Minor change to current component | 1 | 10 | 50 | 62
61 | Calendar/Appointments | Appointments modal |  | New appointments should be able select an horse | Nice to have | USP | Minor change to current component | 1 | 10 | 50 | 63
64 | Finance - Invoicing | Invoice view |  | The detail should reference the horse | Nice to have | USP | Minor change to current component | 1 | 10 | 50 | 61
40 | Calendar/Appointments | Calendar |  | Not able to scroll down the calendar when required | Does not function as expected | Improved UX | Investigation and change | 8 | 4 | 42.6667 |  | Done
1 | Marketing | Landing Page | Landing Section with call to action | Landing page with a call to action - good examples would be www.intch.org and www.monday.com | Poor UX | New feature | New component/service with simple integration | 4 | 7 | 39.2 |  | Done
2 | Marketing | Landing Page | Our Features Section | Should be added to Landing page | Poor UX | New feature | New component/service with simple integration | 4 | 7 | 39.2
4 | Marketing | Landing Page | Client Feedback Section | Should be added to Landing page | Poor UX | New feature | New component/service with simple integration | 4 | 7 | 39.2
5 | Marketing | Landing Page | Footer bar | Should be added to Landing page | Poor UX | New feature | New component/service with simple integration | 4 | 7 | 39.2
24 | User Management | Sign in Modal | User details modal | After registering - User should be presented with a basis users detail form with: First name Last name Contact number User should also presented the option to skip Should be place on top of the main menu page (for now - will be replaced by dash board) | Poor UX | New feature | New component/service with simple integration | 4 | 7 | 39.2
19 | Marketing | Landing Page | What's New Section | Should be added to Landing page | Poor UX | New feature | New component/service with simple integration | 4 | 7 | 39.2
7 | User Management | Sign in Modal |  | Needs to be above the landing page with a sheath background | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32
9 | User Management | Sign in Modal | Login error warnings | Sign in - User not found | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8
10 | User Management | Sign in Modal | Login error warnings | Sign in - Wrong password | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8
11 | User Management | Sign in Modal | Login error warnings | Sign in - Invalid email | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8
12 | User Management | Sign in Modal | Login error warnings | Sign in - Other | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8
13 | User Management | Register modal | Register error warnings | Register - Email already in use | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8
14 | User Management | Register modal | Register error warnings | Register - Invalid email | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8
15 | User Management | Register modal | Register error warnings | Register - Weak password | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8
16 | User Management | Register modal | Register error warnings | Register - Other | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8
23 | User Management | Register modal |  | Clicking Register should warn user before it does | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32
31 | Navbar | Drop down menu |  | The menu hamburger should not be available if on the main menu (make no sense) | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32
34 | Navbar | Drop down menu | Log out | Menu should have a log out option | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32
54 | Calendar/Appointments | Appointments modal |  | Invoices appointments should display the invoice number when the details are views - not to be edited | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32
55 | Calendar/Appointments | Calendar |  | Invoiced appointments should be marked in some way (consider an asterisk) | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32
58 | Finance - Invoicing | Invoice view |  | Should show a Pre-tax sub-total Tax (vat) line A grand total line | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32
67 | Finance - Invoicing | Invoice view |  | Should have an option to go back to the invoice list | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32
84 | Clients | Client lists |  | When clicking the client - it should open the modal as it does now, but in view only mode | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32
89 | Clients | Client lists |  | Should have an option to add a new client on this list | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32
107 | Finance - Payments | Payment list |  | Should be able to toggle view to see voided payments or not (default without) | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32
108 | Clients | Client lists |  | Should be able to toggle view to see voided "archived" clients or not (default without) | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32
109 | User Management | Sign in Modal | Login error warnings | auth/network-request-failed | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8
115 | User Management | Register modal | Register error warnings | Passwords don't match | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8
8 | User Management | Sign in Modal | Login error warnings | Error modals | Poor UX | New feature | New component/service with complex integration | 4 | 7 | 28
22 | User Management | Sign in Modal |  | On small devices the inputs on the modal are mis-aligned (Use 340*635 spec) | Poor UI | Improved UI | Minor tweak | 3 | 3 | 27
43 | Calendar/Appointments | Calendar |  | The heights of the appointment blocks should match there duration | Poor UI | Feature enhancement/fix | Major change to current component | 3 | 6 | 27
44 | Calendar/Appointments | Calendar |  | When too many appointment in a slot - the blocks become cramped… need to find a more elegant way to stack appointment blocks when there are too many appointments | Poor UI | Feature enhancement/fix | Major change to current component | 3 | 6 | 27
48 | Calendar/Appointments | Appointments modal |  | The cancel changes button on and edited appointment should be darker | Poor UI | Improved UI | Minor tweak | 3 | 3 | 27
57 | Finance - Invoicing | Invoice view |  | Lesson (and other sub headings) should be underlined | Poor UI | Improved UI | Minor tweak | 3 | 3 | 27
106 | General |  |  | Update favicon with new logo | Poor UI | Improved UI | Minor tweak | 3 | 3 | 27 |  | Done
49 | Calendar/Appointments | Appointments modal |  | When changes are made - the save button appears - but it should always appear - just be disabled | Poor UX | Improved UX | Investigation and change | 4 | 4 | 21.3333
74 | Finance - Invoicing | Generate invoices | Generate invoices params | On smaller screens you can see the whole modal and scroll down | Poor UX | Improved UX | Investigation and change | 4 | 4 | 21.3333
79 | Finance - Payments | Payment modal |  | On viewing a payment - When trying to record a new payment - the details of the old payment are brought up (as well at the void button) | Poor UX | Improved UX | Investigation and change | 4 | 4 | 21.3333
80 | Finance - Invoicing | Invoice view |  | On the statement when you click an invoice - you view the invoice detail - but when you click back it doesn't take you to the statement | Poor UX | Improved UX | Investigation and change | 4 | 4 | 21.3333
81 | Finance - Payments | Payment modal |  | On the statement when you click an payment - you view the payment modal - but when you click back it doesn't take you to the statement | Poor UX | Improved UX | Investigation and change | 4 | 4 | 21.3333
87 | Clients | Client modal |  | On viewing a client - When trying to record a new client - the details of the old client are brought up | Poor UX | Improved UX | Investigation and change | 4 | 4 | 21.3333
88 | Clients | Client modal |  | On cancelling adding a new client, should take you menu not the list (if you can from the menu) | Poor UX | Improved UX | Investigation and change | 4 | 4 | 21.3333
17 | User Management | Sign in Modal | Forgot password | No way for users to reset forgotten passwords | Poor UX | Feature enhancement/fix | New component/service with complex integration | 4 | 6 | 20.5714
18 | User Management | Sign in Modal | Forgot password | Third party login - Facebook | Poor UX | Feature enhancement/fix | New component/service with complex integration | 4 | 6 | 20.5714
19 | User Management | Sign in Modal | Forgot password | Third party login - Google | Poor UX | Feature enhancement/fix | New component/service with complex integration | 4 | 6 | 20.5714
20 | User Management | Sign in Modal | Forgot password | Third party login - LinkedIn | Poor UX | Feature enhancement/fix | New component/service with complex integration | 4 | 6 | 20.5714
21 | User Management | Sign in Modal | Forgot password | Third party login - Microsoft | Poor UX | Feature enhancement/fix | New component/service with complex integration | 4 | 6 | 20.5714
66 | Finance - Invoicing | Invoice view |  | On clicking the lesson on the viewed invoice - Should bring up the appointment modal - with no option to edit | Nice to have | Feature enhancement/fix | Minor change to current component | 1 | 6 | 18
76 | Finance - Payments | Payment view |  | On clicking the payment on the payment list - Should the payment modal in view only mode | Nice to have | Feature enhancement/fix | Minor change to current component | 1 | 6 | 18
73 | Finance - Invoicing | Generate invoices | Generate invoices params | The generate invoices button should not be available if the form is not completed correctly | Poor UX | Improved UX | Major change to current component | 4 | 4 | 16
91 | Finance - Reports | Report - Review by instructor |  | Required to be built | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 59
92 | Finance - Reports | Report - Review by horse |  | Required to be built | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 64
93 | Finance - Reports | Report - Expenses by instructor |  | Required to be built | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 59
94 | Finance - Reports | Report - Expenses by horse |  | Required to be built | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 64
95 | Finance - Reports | Report - Contribution by instructor |  | Required to be built | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 59
96 | Finance - Reports | Report - Contribution by horse |  | Required to be built | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 64
97 | Finance - Accounting | Bank statement importer |  | If expenses are allocated to instructors should be able to allocate per instructor | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 59
98 | Finance - Accounting | Bank statement importer |  | If expenses are allocated to instructors should be able to allocate per instructor | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 64
100 | Clients | Lesson booking platform |  | On adding a new client - the client needs to be sent and email/SMS/text with a link to where they can book their own lessons | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 99
101 | Clients | Lesson booking platform |  | Client should be able to add themselves as a new client - when on the booking platform | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 100
103 | Finance - Accounting | Statement runs |  | Should be able perform a link batch disperse where the use is sent a link to where their invoices can be found on the platform | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 102
104 | Finance - Accounting | Statement runs |  | Should be able to email the documents and statements to the client | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 103
35 | Navbar | Drop down menu |  | Should not down the screen - but should hover above the current screen content | Poor UI | Improved UI | Minor change to current component | 3 | 3 | 13.5
38 | Calendar/Appointments | Calendar |  | On taller screens - the schedule slots should be have a great height to fill the remainder of the screen | Poor UI | Improved UI | Minor change to current component | 3 | 3 | 13.5
71 | Finance - Invoicing | Generate invoices | Generate invoices params | The radio should be better group - they are too far apart to make sense | Poor UI | Improved UI | Minor change to current component | 3 | 3 | 13.5
72 | Finance - Invoicing | Generate invoices | Generate invoices params | Group of buttons should have a little border to show better relations logic | Poor UI | Improved UI | Minor change to current component | 3 | 3 | 13.5
85 | Clients | Client lists |  | List on smaller screens are squashed | Poor UI | Improved UI | Minor change to current component | 3 | 3 | 13.5
86 | Clients | Client lists |  | Lines on the list should have alternating colours | Poor UI | Improved UI | Minor change to current component | 3 | 3 | 13.5
36 | Dashboard and Main Menu | Main menu | Log out | On clicking logout - should warn user before doing so | Poor UX | Improved UX | New component/service with simple integration | 4 | 4 | 12.8
37 | Navbar | Drop down menu | Log out | On clicking logout - should warn user before doing so | Poor UX | Improved UX | New component/service with simple integration | 4 | 4 | 12.8
47 | Calendar/Appointments | Appointments modal | Cancelling/Voiding | Cancelling the appointment should warn the user before the appointment is actually cancelled | Poor UX | Improved UX | New component/service with simple integration | 4 | 4 | 12.8
50 | Calendar/Appointments | Appointments modal | Cancelling/Voiding | On cancelling a new appointment (after changes are made) should warn the user that changes will be lost | Poor UX | Improved UX | New component/service with simple integration | 4 | 4 | 12.8
56 | Calendar/Appointments | Appointments modal |  | When cancelling an invoiced appoint and additional warning of the credit not needs to be provided | Poor UX | Improved UX | New component/service with simple integration | 4 | 4 | 12.8
41 | Calendar/Appointments | Calendar | Your calendar drop down | The your calendar header should be a drop down that allows the user to see other staff members calendars The drop down menu should be multi select The differently coloured appointment blocks should have a border indicating whose calendar the appointment is from | Nice to have | USP | Whole new feature | 1 | 10 | 12.5
52 | Finance - Payments | Bulk uploads |  | Should be able to bulk upload payments Should have a standard template Should remember the reference - and assign based on that (where this has been seen before) | Nice to have | USP | Whole new feature | 1 | 10 | 12.5
65 | Finance - Invoicing | PDF export |  | Should be able to export the invoice to PDF Will required a lot more client and company detail Should ask the user where to save it | Nice to have | USP | Whole new feature | 1 | 10 | 12.5
83 | Finance - Reports | Profit and lose report |  | Mini profit and loss report Should be able to select for a period | Nice to have | USP | Whole new feature | 1 | 10 | 12.5
102 | Finance - Accounting | Statement runs |  | Client should be able to perform a statement run with a simple flow process All clients statements are to be PDDd and saved to their folder along with their backing fin documents (invoice, credit notes etc , payment receipts) User should be able to determine where the batch of documents is saved | Nice to have | USP | Whole new feature | 1 | 10 | 12.5
105 | User Management | Profile portal |  | A portal where the client can Update their details Add new users to their account Any other preferences they want | Nice to have | USP | Whole new feature | 1 | 10 | 12.5
33 | Dashboard and Main Menu | Dashboard |  | New page: Dashboard Should only be available on desktop Should have a option to go to the main menu Will contain a variety of reports and summaries | Nice to have | USP | Whole new section | 1 | 10 | 10
62 | Equipment/Assets |  |  | New section required to add instructor to the client | Nice to have | USP | Whole new section | 1 | 10 | 10
63 | Staff management |  |  | New section required to add horse to the client | Nice to have | USP | Whole new section | 1 | 10 | 10
82 | Finance - Accounting | Bank statement importer |  | Should be able import a bank statement: Would require use to allocate transactions Transaction are to be remembered for future use Should perform a quick recon calculation Expenses should be able to be captured when paid (Later will be done on a invoice basis and then payments are allocated to supplier dues) | Nice to have | USP | Whole new section | 1 | 10 | 10
99 | Booking | Lesson booking platform |  | A platform where a customer of the client can book their lessons, based on the slots the client has deemed and allowed as open | Nice to have | USP | Whole new section | 1 | 10 | 10
26 | Dashboard and Main Menu | Main menu |  | As the screen gets wider - the buttons tend to lower - needs to be consistent | Poor UI | Improved UI | Investigation and change | 3 | 3 | 9
39 | Calendar/Appointments | Calendar |  | On shorter screens - Schedule slot should have a minimum height | Poor UI | Improved UI | Investigation and change | 3 | 3 | 9
42 | Calendar/Appointments | Appointments modal |  | On smaller screens the Date input is too far right | Poor UI | Improved UI | Investigation and change | 3 | 3 | 9
46 | Calendar/Appointments | Appointments modal |  | On smaller screen the alignments need to be improved - specifically in the view only mode | Poor UI | Improved UI | Investigation and change | 3 | 3 | 9
68 | Finance - Invoicing | Invoice list |  | Should have the ability to filter the list | Nice to have | Feature enhancement/fix | Major change to current component | 1 | 6 | 9
69 | Finance - Invoicing | Invoice list |  | Should have the ability to sort the list | Nice to have | Feature enhancement/fix | Major change to current component | 1 | 6 | 9
70 | Finance - Invoicing | Invoice list |  | List should be paginated | Nice to have | Feature enhancement/fix | Major change to current component | 1 | 6 | 9
75 | Finance - Invoicing | Generate invoices | Generate invoices results | Needs to produce a summary of the invoices generated: Number of invoices Lessons invoices Total revenue Average revenue per invoices Median invoice revenue Largest and smallest invoices by revenue | Nice to have | Feature enhancement/fix | Major change to current component | 1 | 6 | 9
78 | Finance - Payments | Payment modal |  | Payments should have a Type property (EFT vs Cash) | Nice to have | Feature enhancement/fix | Major change to current component | 1 | 6 | 9
110 | General |  |  | Modal screens are still scrollable - when the sheath should prevent that | Poor UI | Improved UI | Investigation and change | 3 | 3 | 9
51 | General | Warnings |  | Warnings should have an option to allow users to not see them again | Nice to have | New feature | New component/service with complex integration | 1 | 7 | 7
28 | Dashboard and Main Menu | Main menu |  | There should be a view for desktop where the button become a grid of square buttons with icons | Poor UI | Improved UI | Major change to current component | 3 | 3 | 6.75
111 | Finance - Invoicing | Generate invoices |  | Invoices do not need a voided property as they can't be voided - only credit noted | Poor UX | Refactor/Tech debt | Minor change to current component | 4 | 1 | 2
29 | Dashboard and Main Menu | Main menu |  | Needs to use the new view service to determine its required state | Poor UI | Refactor/Tech debt | Minor change to current component | 3 | 1 | 1.5 | 27
30 | Navbar |  |  | Needs to use the new view service to determine its required state | Poor UI | Refactor/Tech debt | Minor change to current component | 3 | 1 | 1.5 | 27
27 | General | Utility services |  | There needs to be a service that determine whether the view should be mobile or desktop | Poor UI | Refactor/Tech debt | New component/service with complex integration | 3 | 1 | 0.42857