## Sheet2
App
| Module 1 | [9 empty] | Module 2
|  | Routing Config : Mobile |  |  |  | Routing Config : Tablet |  |  | Routing Config : Desktop |  |  | Common Routing Config for all screen sizes
|  |  | Page 1 | Page 2 | Page 3 |  | Page 1 | Page 2 |  | Page 1 |  |  | Page 1
[14 empty] | View State 1 |  |  | View State 2
[16 empty] | Screen |  | Component 1
Component 1
Component 2
Component 1
Modal
Modal

## Summary of completion
Column Labels
| Done | N/A | To do | Grand Total
Sum of Priority S | 1949.4 | 124.5333 | 1153.6643 | 3227.5976
64.26%
Column Labels
| Done | N/A | To do | Grand Total
Sum of Importance S | 191 | 16 | 165 | 372
55.65%
Column Labels
| Done | N/A | To do | Grand Total
Sum of Impact S | 195 | 19 | 466 | 680
31.47%

## Source lists
Sections | Features | Sub-Feature | Importance | Score | Impact |  | Complexity
Calendar/Appointments | Appointments modal | Cancelling/Voiding | Breaks App | 10 | USP | 10 | Whole new section | 10
Clients | Bank statement importer | Client Feedback Section | Does not function as expected | 8 | New feature | 7 | Whole new feature | 8
Dashboard and Main Menu | Bulk uploads | Date picker | Poor UX | 4 | Feature enhancement/fix | 6 | New component/service with complex integration | 7
Finance - Accounting | Calendar | Footer bar | Poor UI | 3 | Improved UX | 4 | New component/service with simple integration | 5
Finance - Invoicing | Client lists | Forgot password | Nice to have | 1 | Improved UI | 3 | Major change to current component | 4
Finance - Payments | Client modal | Generate invoices parms |  |  | Refactor/Tech debt | 1 | Investigation and change | 3
Finance - Reports | Dashboard | Generate invoices results |  |  |  |  | Minor change to current component | 2
General | Drop down menu | Landing Section with call to action |  |  |  |  | Minor tweak | 1
Lifestock management | Generate invoices | Log out
Marketing | Invoice list | Login error warnings
Navbar | Invoice view | Features Section
Staff management | Landing Page | Register
User Management | Login Button | Third party login
Booking | Logo | User details modal
Login/Register | Main menu | What's New Section
| Payment list | Your calendar drop down
| Payment modal | Register error warnings
| PDF export | Why us section
Report - Profit and lose
Sign in Modal
Utility services
Warnings
Report - Review by instructor
Report - Review by horse
Report - Expenses by instructor
Report - Expenses by horse
Report - Contribution by instructor
Report - Contribution by horse
Lesson booking platform
Statement runs
Profile portal
Register modal

## Issues 3-1-24
# | Section | Features | Sub-Feature | Description | Importance | Impact | Complexity | Importance S | Impact S | Priority S | Dependency # | Dep status | Status
53 | Calendar/Appointments | Appointments modal | Cancelling/Voiding | If an appointment is cancelled but that have been previously invoiced - then this needs to be credit noted | Does not function as expected | USP | Major change to current component | 8 | 10 | 200 | 77 | Done | Done
6 | Navbar | Login Button |  | Should be added to Navbar | Poor UX | New feature | Minor change to current component | 4 | 7 | 98 | 1 | Done | Done
77 | Finance - Payments | Payment modal |  | Voiding payments does not work | Does not function as expected | Feature enhancement/fix | Investigation and change | 8 | 6 | 96 |  |  | Done
90 | Clients | Client modal |  | Remove client is not working | Does not function as expected | Feature enhancement/fix | Investigation and change | 8 | 6 | 96 |  |  | Done
112 | Finance - Reports | Statement runs |  | Statements do not show credit notes (where required) | Does not function as expected | Feature enhancement/fix | Investigation and change | 8 | 6 | 96 | 53 | Done | Done
114 | Finance - Payments | Payment modal |  | Payment are not being recorded correctly | Does not function as expected | Feature enhancement/fix | Investigation and change | 8 | 6 | 96 |  |  | Done
45 | Calendar/Appointments | Calendar | Date picker | Should have a date picker at the top of the calendar | Poor UX | Feature enhancement/fix | Minor change to current component | 4 | 6 | 72 |  |  | Done
116 | Marketing | Landing Page | Our Features Section | Update content for the features section of the landing page | Poor UX | Feature enhancement/fix | Minor change to current component | 4 | 6 | 72 | 2 | Done | Done
32 | Navbar | Logo |  | On hovering the logo the cursor should be pointer | Poor UX | Improved UX | Minor tweak | 4 | 4 | 64 |  |  | Done
113 | Login/Register | Register modal |  | Needs to be a modal specfically for registrations | Does not function as expected | Feature enhancement/fix | New component/service with simple integration | 8 | 6 | 57.6 |  |  | Done
25 | User Management | Sign in Modal |  | After trying to register (and assuming it fails) and attempts in future to sign in will result in a registration attempt | Breaks App | Improved UX | Investigation and change | 10 | 4 | 53.3333 |  |  | Done
59 | Finance - Invoicing | Invoice view |  | The detail should reference the instructor | Nice to have | USP | Minor change to current component | 1 | 10 | 50 | 60 | To do | To do
60 | Calendar/Appointments | Appointments modal |  | New appointments should be able select an instructor | Nice to have | USP | Minor change to current component | 1 | 10 | 50 | 62 | To do | To do
61 | Calendar/Appointments | Appointments modal |  | New appointments should be able select an horse | Nice to have | USP | Minor change to current component | 1 | 10 | 50 | 63 | To do | To do
64 | Finance - Invoicing | Invoice view |  | The detail should reference the horse | Nice to have | USP | Minor change to current component | 1 | 10 | 50 | 61 | To do | To do
40 | Calendar/Appointments | Calendar |  | Not able to scroll down the calendar when required | Does not function as expected | Improved UX | Investigation and change | 8 | 4 | 42.6667 |  |  | Done
1 | Marketing | Landing Page | Landing Section with call to action | Landing page with a call to action - good examples would be www.intch.org and www.monday.com | Poor UX | New feature | New component/service with simple integration | 4 | 7 | 39.2 |  |  | Done
2 | Marketing | Landing Page | Features Section | Should be added to Landing page | Poor UX | New feature | New component/service with simple integration | 4 | 7 | 39.2 |  |  | Done
4 | Marketing | Landing Page | Client Feedback Section | Should be added to Landing page | Poor UX | New feature | New component/service with simple integration | 4 | 7 | 39.2 |  |  | Done
17 | Marketing | Landing Page | What's New Section | Should be added to Landing page | Poor UX | New feature | New component/service with simple integration | 4 | 7 | 39.2 |  |  | Done
24 | User Management | Sign in Modal | User details modal | After registering - User should be presented with a basic users detail form with: First name Last name Contact number User should also presented the option to skip Should be place on top of the main menu page (for now - will be replaced by dash board) | Poor UX | New feature | New component/service with simple integration | 4 | 7 | 39.2 |  |  | N/A
9 | User Management | Sign in Modal | Login error warnings | Sign in - User not found | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8 | Done | Done
10 | User Management | Sign in Modal | Login error warnings | Sign in - Wrong password | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8 | Done | Done
11 | User Management | Sign in Modal | Login error warnings | Sign in - Invalid email | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8 | Done | Done
12 | User Management | Sign in Modal | Login error warnings | Sign in - Other | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8 | Done | Done
13 | User Management | Register modal | Register error warnings | Register - Email already in use | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8 | Done | Done
14 | User Management | Register modal | Register error warnings | Register - Invalid email | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8 | Done | Done
15 | User Management | Register modal | Register error warnings | Register - Weak password | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8 | Done | Done
16 | User Management | Register modal | Register error warnings | Register - Other | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8 | Done | Done
23 | User Management | Register modal |  | Clicking Register should warn user before it does | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 |  |  | Done
115 | User Management | Register modal | Register error warnings | Passwords don't match | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8 | Done | Done
7 | User Management | Sign in Modal |  | Needs to be above the landing page with a sheath background | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 |  |  | N/A
34 | Navbar | Drop down menu | Log out | Menu should have a log out option | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 |  |  | Done
54 | Calendar/Appointments | Appointments modal |  | Invoiced appointments should display the invoice number when the details are viewed - not to be editable | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 |  |  | Done
55 | Calendar/Appointments | Calendar |  | Invoiced appointments should be marked in some way (consider an asterisk) | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 |  |  | Done
58 | Finance - Invoicing | Invoice view |  | Should show a Pre-tax sub-total Tax (vat) line A grand total line | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 |  |  | Done
67 | Finance - Invoicing | Invoice view |  | Should have an option to go back to the invoice list | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 |  |  | Done
84 | Clients | Client lists |  | When clicking the client - it should open the modal as it does now, but in view only mode | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 |  |  | Done
89 | Clients | Client lists |  | Should have an option to add a new client on this list | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 |  |  | Done
107 | Finance - Payments | Payment list |  | Should be able to toggle view to see voided payments or not (default without) | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 |  |  | Done
108 | Clients | Client lists |  | Should be able to toggle view to see voided "archived" clients or not (default without) | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 |  |  | Done
109 | User Management | Sign in Modal | Login error warnings | auth/network-request-failed | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 | 8 | Done | Done
31 | Navbar | Drop down menu |  | The menu hamburger should not be available if on the main menu (make no sense) | Poor UX | Improved UX | Minor change to current component | 4 | 4 | 32 |  |  | N/A
17 | Marketing | Landing Page | Why us section | Should be added to Landing page | Poor UI | New feature | New component/service with simple integration | 3 | 7 | 29.4 |  |  | To do
8 | User Management | Sign in Modal | Login error warnings | Error modals | Poor UX | New feature | New component/service with complex integration | 4 | 7 | 28 |  |  | Done
106 | General |  |  | Update favicon with new logo | Poor UI | Improved UI | Minor tweak | 3 | 3 | 27 |  |  | Done
22 | User Management | Sign in Modal |  | On small devices the inputs on the modal are mis-aligned (Use 340*635 spec) | Poor UI | Improved UI | Minor tweak | 3 | 3 | 27 |  |  | Done
48 | Calendar/Appointments | Appointments modal |  | The cancel changes button on and edited appointment should be darker | Poor UI | Improved UI | Minor tweak | 3 | 3 | 27 |  | Done | To do
43 | Calendar/Appointments | Calendar |  | The heights of the appointment blocks should match their duration | Poor UI | Feature enhancement/fix | Major change to current component | 3 | 6 | 27 |  |  | To do
44 | Calendar/Appointments | Calendar |  | When too many appointment in a slot - the blocks become cramped… need to find a more elegant way to stack appointment blocks when there are too many appointments | Poor UI | Feature enhancement/fix | Major change to current component | 3 | 6 | 27 |  |  | To do
57 | Finance - Invoicing | Invoice view |  | Lesson (and other sub headings) should be underlined | Poor UI | Improved UI | Minor tweak | 3 | 3 | 27 |  |  | Done
49 | Calendar/Appointments | Appointments modal |  | When changes are made - the save button appears - but it should always appear - just be disabled | Poor UX | Improved UX | Investigation and change | 4 | 4 | 21.3333 |  |  | To do
88 | Clients | Client modal |  | On cancelling adding a new client, should take you menu not the list (if you can from the menu) | Poor UX | Improved UX | Investigation and change | 4 | 4 | 21.3333 |  |  | To do
74 | Finance - Invoicing | Generate invoices | Generate invoices params | On smaller screens you can see the whole modal and scroll down | Poor UX | Improved UX | Investigation and change | 4 | 4 | 21.3333 |  |  | To do
80 | Finance - Invoicing | Invoice view |  | On the statement when you click an invoice - you view the invoice detail - but when you click back it doesn't take you to the statement | Poor UX | Improved UX | Investigation and change | 4 | 4 | 21.3333 |  |  | To do
79 | Finance - Payments | Payment modal |  | On viewing a payment - When trying to record a new payment - the details of the old payment are brought up (as well at the void button) | Poor UX | Improved UX | Investigation and change | 4 | 4 | 21.3333 |  |  | To do
87 | Clients | Client modal |  | On viewing a client - When trying to record a new client - the details of the old client are brought up | Poor UX | Improved UX | Investigation and change | 4 | 4 | 21.3333 |  |  | N/A
81 | Finance - Payments | Payment modal |  | On the statement when you click an payment - you view the payment modal - but when you click back it doesn't take you to the statement | Poor UX | Improved UX | Investigation and change | 4 | 4 | 21.3333 |  |  | To do
17 | User Management | Sign in Modal | Forgot password | No way for users to reset forgotten passwords | Poor UX | Feature enhancement/fix | New component/service with complex integration | 4 | 6 | 20.5714 |  |  | To do
18 | User Management | Sign in Modal | Third party login | Third party login - Facebook | Poor UX | Feature enhancement/fix | New component/service with complex integration | 4 | 6 | 20.5714 |  |  | To do
19 | User Management | Sign in Modal | Third party login | Third party login - Google | Poor UX | Feature enhancement/fix | New component/service with complex integration | 4 | 6 | 20.5714 |  |  | To do
20 | User Management | Sign in Modal | Third party login | Third party login - LinkedIn | Poor UX | Feature enhancement/fix | New component/service with complex integration | 4 | 6 | 20.5714 |  |  | To do
21 | User Management | Sign in Modal | Third party login | Third party login - Microsoft | Poor UX | Feature enhancement/fix | New component/service with complex integration | 4 | 6 | 20.5714 |  |  | To do
66 | Finance - Invoicing | Invoice view |  | On clicking the lesson on the viewed invoice - Should bring up the appointment modal - with no option to edit | Nice to have | Feature enhancement/fix | Minor change to current component | 1 | 6 | 18 |  |  | To do
76 | Finance - Payments | Payment view |  | On clicking the payment on the payment list - Should the payment modal in view only mode | Nice to have | Feature enhancement/fix | Minor change to current component | 1 | 6 | 18 |  |  | To do
73 | Finance - Invoicing | Generate invoices | Generate invoices params | The generate invoices button should not be available if the form is not completed correctly | Poor UX | Improved UX | Major change to current component | 4 | 4 | 16 |  |  | To do
91 | Finance - Reports | Report - Review by instructor |  | Required to be built | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 59 | To do | To do
92 | Finance - Reports | Report - Review by horse |  | Required to be built | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 64 | To do | To do
93 | Finance - Reports | Report - Expenses by instructor |  | Required to be built | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 59 | To do | To do
94 | Finance - Reports | Report - Expenses by horse |  | Required to be built | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 64 | To do | To do
95 | Finance - Reports | Report - Contribution by instructor |  | Required to be built | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 59 | To do | To do
96 | Finance - Reports | Report - Contribution by horse |  | Required to be built | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 64 | To do | To do
97 | Finance - Accounting | Bank statement importer |  | If expenses are allocated to instructors should be able to allocate per instructor | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 59 | To do | To do
98 | Finance - Accounting | Bank statement importer |  | If expenses are allocated to instructors should be able to allocate per instructor | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 64 | To do | To do
100 | Clients | Lesson booking platform |  | On adding a new client - the client needs to be sent and email/SMS/text with a link to where they can book their own lessons | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 99 | To do | To do
101 | Clients | Lesson booking platform |  | Client should be able to add themselves as a new client - when on the booking platform | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 100 | To do | To do
103 | Finance - Accounting | Statement runs |  | Should be able perform a link batch disperse where the use is sent a link to where their invoices can be found on the platform | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 102 | To do | To do
104 | Finance - Accounting | Statement runs |  | Should be able to email the documents and statements to the client | Nice to have | USP | New component/service with complex integration | 1 | 10 | 14.2857 | 103 | To do | To do
38 | Calendar/Appointments | Calendar |  | On taller screens - the schedule slots should be have a great height to fill the remainder of the screen | Poor UI | Improved UI | Minor change to current component | 3 | 3 | 13.5 |  | Done | To do
85 | Clients | Client lists |  | List on smaller screens are squashed | Poor UI | Improved UI | Minor change to current component | 3 | 3 | 13.5 |  |  | To do
86 | Clients | Client lists |  | Lines on the list should have alternating colours | Poor UI | Improved UI | Minor change to current component | 3 | 3 | 13.5 |  |  | To do
71 | Finance - Invoicing | Generate invoices | Generate invoices params | The radio should be better group - they are too far apart to make sense | Poor UI | Improved UI | Minor change to current component | 3 | 3 | 13.5 |  |  | To do
72 | Finance - Invoicing | Generate invoices | Generate invoices params | Group of buttons should have a little border to show better relations logic | Poor UI | Improved UI | Minor change to current component | 3 | 3 | 13.5 |  |  | To do
35 | Navbar | Drop down menu |  | Should not down the screen - but should hover above the current screen content | Poor UI | Improved UI | Minor change to current component | 3 | 3 | 13.5 |  |  | To do
47 | Calendar/Appointments | Appointments modal | Cancelling/Voiding | Cancelling the appointment should warn the user before the appointment is actually cancelled | Poor UX | Improved UX | New component/service with simple integration | 4 | 4 | 12.8 |  |  | To do
50 | Calendar/Appointments | Appointments modal | Cancelling/Voiding | On cancelling a new appointment (after changes are made) should warn the user that changes will be lost | Poor UX | Improved UX | New component/service with simple integration | 4 | 4 | 12.8 |  |  | To do
56 | Calendar/Appointments | Appointments modal |  | When cancelling an invoiced appoint and additional warning of the credit not needs to be provided | Poor UX | Improved UX | New component/service with simple integration | 4 | 4 | 12.8 |  |  | To do
36 | Dashboard and Main Menu | Main menu | Log out | On clicking logout - should warn user before doing so | Poor UX | Improved UX | New component/service with simple integration | 4 | 4 | 12.8 |  |  | To do
37 | Navbar | Drop down menu | Log out | On clicking logout - should warn user before doing so | Poor UX | Improved UX | New component/service with simple integration | 4 | 4 | 12.8 |  |  | To do
41 | Calendar/Appointments | Calendar | Your calendar drop down | The your calendar header should be a drop down that allows the user to see other staff members calendars The drop down menu should be multi select The differently coloured appointment blocks should have a border indicating whose calendar the appointment is from | Nice to have | USP | Whole new feature | 1 | 10 | 12.5 | Dependant on staff module having being completed | #N/A | To do
102 | Finance - Accounting | Statement runs |  | Client should be able to perform a statement run with a simple flow process All clients statements are to be PDDd and saved to their folder along with their backing fin documents (invoice, credit notes etc , payment receipts) User should be able to determine where the batch of documents is saved | Nice to have | USP | Whole new feature | 1 | 10 | 12.5 |  |  | To do
65 | Finance - Invoicing | PDF export |  | Should be able to export the invoice to PDF Will required a lot more client and company detail Should ask the user where to save it | Nice to have | USP | Whole new feature | 1 | 10 | 12.5 |  |  | To do
52 | Finance - Payments | Bulk uploads |  | Should be able to bulk upload payments Should have a standard template Should remember the reference - and assign based on that (where this has been seen before) | Nice to have | USP | Whole new feature | 1 | 10 | 12.5 |  |  | To do
83 | Finance - Reports | Profit and lose report |  | Mini profit and loss report Should be able to select for a period | Nice to have | USP | Whole new feature | 1 | 10 | 12.5 |  |  | To do
105 | User Management | Profile portal |  | A portal where the client can Update their details Add new users to their account Any other preferences they want | Nice to have | USP | Whole new feature | 1 | 10 | 12.5 |  |  | To do
99 | Booking | Lesson booking platform |  | A platform where a customer of the client can book their lessons, based on the slots the client has deemed and allowed as open | Nice to have | USP | Whole new section | 1 | 10 | 10 |  |  | To do
33 | Dashboard and Main Menu | Dashboard |  | New page: Dashboard Should only be available on desktop Should have a option to go to the main menu Will contain a variety of reports and summaries | Nice to have | USP | Whole new section | 1 | 10 | 10 |  |  | To do
62 | Equipment/Assets |  |  | New section required to add instructor to the client | Nice to have | USP | Whole new section | 1 | 10 | 10 |  |  | To do
82 | Finance - Accounting | Bank statement importer |  | Should be able import a bank statement: Would require use to allocate transactions Transaction are to be remembered for future use Should perform a quick recon calculation Expenses should be able to be captured when paid (Later will be done on a invoice basis and then payments are allocated to supplier dues) | Nice to have | USP | Whole new section | 1 | 10 | 10 |  |  | To do
63 | Staff management |  |  | New section required to add horse to the client | Nice to have | USP | Whole new section | 1 | 10 | 10 |  |  | To do
5 | Marketing | Landing Page | Footer bar | Should be added to Landing page | Nice to have | New feature | New component/service with simple integration | 1 | 7 | 9.8 |  |  | To do
42 | Calendar/Appointments | Appointments modal |  | On smaller screens the Date input is too far right | Poor UI | Improved UI | Investigation and change | 3 | 3 | 9 |  |  | To do
46 | Calendar/Appointments | Appointments modal |  | On smaller screen the alignments need to be improved - specifically in the view only mode | Poor UI | Improved UI | Investigation and change | 3 | 3 | 9 |  |  | To do
39 | Calendar/Appointments | Calendar |  | On shorter screens - Schedule slot should have a minimum height | Poor UI | Improved UI | Investigation and change | 3 | 3 | 9 |  | Done | To do
26 | Dashboard and Main Menu | Main menu |  | As the screen gets wider - the buttons tend to lower - needs to be consistent | Poor UI | Improved UI | Investigation and change | 3 | 3 | 9 |  |  | To do
75 | Finance - Invoicing | Generate invoices | Generate invoices results | Needs to produce a summary of the invoices generated: Number of invoices Lessons invoices Total revenue Average revenue per invoices Median invoice revenue Largest and smallest invoices by revenue | Nice to have | Feature enhancement/fix | Major change to current component | 1 | 6 | 9 |  |  | To do
68 | Finance - Invoicing | Invoice list |  | Should have the ability to filter the list | Nice to have | Feature enhancement/fix | Major change to current component | 1 | 6 | 9 |  |  | To do
69 | Finance - Invoicing | Invoice list |  | Should have the ability to sort the list | Nice to have | Feature enhancement/fix | Major change to current component | 1 | 6 | 9 |  |  | To do
70 | Finance - Invoicing | Invoice list |  | List should be paginated | Nice to have | Feature enhancement/fix | Major change to current component | 1 | 6 | 9 |  |  | To do
78 | Finance - Payments | Payment modal |  | Payments should have a Type property (EFT vs Cash) | Nice to have | Feature enhancement/fix | Major change to current component | 1 | 6 | 9 |  |  | To do
110 | General |  |  | Modal screens are still scrollable - when the sheath should prevent that | Poor UI | Improved UI | Investigation and change | 3 | 3 | 9 |  |  | To do
51 | General | Warnings |  | Warnings should have an option to allow users to not see them again | Nice to have | New feature | New component/service with complex integration | 1 | 7 | 7 |  |  | To do
28 | Dashboard and Main Menu | Main menu |  | There should be a view for desktop where the button become a grid of square buttons with icons | Poor UI | Improved UI | Major change to current component | 3 | 3 | 6.75 |  |  | To do
111 | Finance - Invoicing | Generate invoices |  | Invoices do not need a voided property as they can't be voided - only credit noted | Poor UX | Refactor/Tech debt | Minor change to current component | 4 | 1 | 2 |  |  | To do
29 | Dashboard and Main Menu | Main menu |  | Needs to use the new view service to determine its required state | Poor UI | Refactor/Tech debt | Minor change to current component | 3 | 1 | 1.5 | 27 | To do | To do
30 | Navbar |  |  | Needs to use the new view service to determine its required state | Poor UI | Refactor/Tech debt | Minor change to current component | 3 | 1 | 1.5 | 27 | To do | To do
27 | General | Utility services |  | There needs to be a service that determine whether the view should be mobile or desktop | Poor UI | Refactor/Tech debt | New component/service with complex integration | 3 | 1 | 0.42857 |  |  | To do

## Initialisation flow
Step 1 | [8 empty] | Step 2
| User action | User action variaion | Logic/Condition checks |  | Service calls | App response | New flow |  | User action | App response | New flow
Start | User navigates to site | To only host url | Is user logged in? |  |  | User taken to landing page with ONLY Dashbaord button | 2A | 2A | User clicks dashboard button | User taken to dashboard page | Dashboard flows
Yes
[6 empty] | User taken to landing page with BOTH Register and Sign in options | 2B |  | User navigates landing page |  | Landing page flows
No
|  | To only host url with a path | Is user logged in? |  |  | User is taken to requested page | Relevent flow based on request path | Start | User clicks register button | User is taken to register page | Sign in / Regsiter flow
Yes
[5 empty] | Navigation service - setReturnPath | User is taken to sign in screen | Sign in / Regsiter flow |  | User clicks sign in button | User is taken to sign in screen | Sign in / Regsiter flow
No
[9 empty] | User navigates landing page |  | Landing page flows

## Sign in and Register flow
Step 1 |  |  |  |  | Step 2 | [9 empty] | Step 3 | [12 empty] | Step 4
| User action | User action variaion | App response | New flow |  | User action | User action variaion | Logic/Condition checks |  |  |  | App response | New flow |  |  | User action | User action variaion | Logic/Condition checks |  |  |  | Service calls | API calls | Response |  | App response | New flow |  | User action | Service calls | API calls | Response |  | App response | New flow
Start | User navigates to Sign in or Register Pages | Sign in | User is taken to sign in screen | 2A | 2A | User fills in Sign in form | Form is COMPLETE WITH NO validaton errors |  | Are all form fields valid |  |  | The Sign in button remains disabled, error messgaes appear | 2A |  | 3A-1 | User clicks Sign In button | [5 empty] | Auth Service - signInUser | afAuth.signInWithEmailAndPassword |  |  | User taken to dashboard page | Dashboard flows | 4A | User clicks Close |  |  |  |  | Error modal closes and user returned the application as they were | 2A/2B
[11 empty] | No | [13 empty] | HTTP 200
|  | Register | User is taken to register page | 2B |  |  | Form is INCOMPLETE with no validaton errors | [7 empty] | 3A-2 | User clicks Register button |  |  | Passwords Match? |  |  | Auth Service - registerUser | this.afAuth.createUserWithEmailAndPassword |  |  | User presented "User Not Found' error modal | 4A | 4B | User clicks "Send reset email" button | Auth Service - sendResetPasswordEmail | this.afAuth.sendPasswordResetEmail |  |  | Forgot password modal closes and user returned the sign in modal | 2B
[10 empty] | Yes | [10 empty] | Yes |  |  |  | auth/user-not-found | [7 empty] | HTTP 200
[7 empty] | Form is COMPLETE WITH validaton errors |  | Are all fields completed | [10 empty] | No | [5 empty] | User presented "Wrong Password' error modal | [7 empty] | User presented "Failed to send email' error modal | 4A
[11 empty] | No | [13 empty] | auth/wrong-password | [7 empty] | Any other error
[7 empty] | Form is INCOMEPLETE WITH NO validaton errors |  |  |  |  | The Sign in button (formerly disabled) becomes enabled | 3A-1 | The Sign in button remains disabled, error messgaes appear | [11 empty] | User presented "Email already registered error modal
[10 empty] | Yes | [14 empty] | auth/email-already-in-use
[6 empty] | User clicks Third party auth login | [5 empty] | User is presented with third party sign in modal | 3B-2 | [12 empty] | User presented "Network erro' error modal
auth/network-request-failed
[6 empty] | User clicks "Forgot password" | [5 empty] | User is presented with Forgot Password modal | 3C | [12 empty] | User presented "Unspecified Error' error modal
Any other error
[6 empty] | User clicks Register | [5 empty] | User navigates to Register page | 2B | [12 empty] | Register from shows fields errors "Passwords do not match" | 2B
[5 empty] | 2B | User fills in New Registration form | Form is COMPLETE WITH NO validaton errors |  | Are all form fields valid |  |  | The Register button remains disabled, error messgaes appear | 2B |  | 3B-1 | User proceeds through Third Party Sign in | User completes process | You create a new user in your Firebase project by calling the createUserWithEmailAndPassword method or by signing in a user for the first time using a federated identity provider, such as Google Sign-In or Facebook Login. |  |  |  | Auth Service - thirdPartySignIn | afAuth.signInWithPopup |  |  | User taken to dashboard page | Dashboard flows
[11 empty] | No | [13 empty] | HTTP 200
[7 empty] | Form is incoINCOMPLETE with no validaton errors | [7 empty] | 3B-2 | User proceeds through Third Party Registration | User abandons process | [8 empty] | User presented "Unspecified Error' error modal | 4A
[10 empty] | Yes | [14 empty] | Any other error
[7 empty] | Form is COMPLETE WITH validaton errors |  | Are all fields completed | [16 empty] | Third party modal closes and user returned the application as they were | 2A/2B
No
[7 empty] | Form is INCOMEPLETE WITH NO validaton errors |  |  |  |  | The Sign in button (formerly disabled) becomes enabled | 3A-2 |  | 3C | User enters email | Provides VALID email | [8 empty] | The "Send reset email" button (formerly disabled) becomes enabled | 4B
Yes
[6 empty] | User clicks Third party auth regitration | [5 empty] | User is presented with third party register modal | 3B-2 |  |  |  | Provides INVALID email | [8 empty] | The "Send reset email" button remains disabled, error messgaes appear | 3C
[6 empty] | User clicks Sign in | [5 empty] | User navigates to Sign in page | 2A |  |  | User clicks cancel | [9 empty] | Forgot password modal closes and user returned the sign in modal | 2A

## Requirements for Launch
Module | An independent module that would be effectively an entire part of the application website. Such module would contain custom routing configurations for each view (a view being Mobile/Tablet/Desktop), but may also only have a single routing configuration for all views if the underlying pages are build well enough
Module Routing Configuration | Because some screen sizes are able to contain more content then others (Desktop vs Mobile), smaller screen sizes may require that a Page within a module for a larger view be broken down into separate pages with in smaller screen sizes.
Page | With in the Module Routing Configuration - Each route provided will be linked to a component being a Page. The Page is made up of ViewStates - which themselves can be futher broken down.
View states | A Page's ViewStates are state the page can take based on various conditions. Each ViewState will then be made up of a single or multiple Sections (eg Sign in Page may have the standard Sign In ViewState which be switched to the Forgot Password View State - so the screen content completely changes - but the url does not). A page may have a single ViewState or multiple ViewStates.
Section | A ViewState may contain a single Section or a multiple of Sections for more complex pages such as Dashboard ViewStates that may contain various Sections (Widgets) with different bits of information provided to a user in a single page
Components | The component(s) embedded into a section - typlically are pre-built in the library
Modals | A component that able to render over or replace the content of a section - if that section calls up the modal - typlically are pre-built in the library
Screen | Where a section is commonly built - the library may have a pre-build section that can be simply imported into the parent view. This screen would then contain the required components and modals
Module | Routing config | Page | ViewState | Section | Screen/Component/Modal
Landing | Common for all screen sizes | LandingPage | MAIN | Entry and C2A | Screen - Landing - Call to Action
|  |  |  | Features | Screen - Landing - Structured content
|  |  |  | Client testimonials | Screen - Landing - Structured content
|  |  |  | Why us | Screen - Landing - Structured content
|  |  |  | Whats new | Screen - Landing - Structured content
|  |  |  | Footer | Screen - Landing - Structured footer
Auth | Common for all screen sizes | SignInPage | FORM | - | Modal - Sign in
|  |  | FORGOT_PASSWORD | - | Modal - Forgot password
|  |  | ERROR | - | Modal - Auth Error states
|  | RegisterPage | FORM | - | Modal - Register
|  |  | ERROR | - | Modal - Auth Error states
Dashboard | Common for all screen sizes | Dashboard Page | MOBILE | Header with settings | Todays Lessons
Upcoming lessons
Mini-Calendar
Mini P/L
Debtors
Up coming lifestock treatments
Menu
Setting Modal
Mobile
Tablet
Desktop
Clients | Mobile
Tablet
Desktop
Finance | Mobile
Tablet
Desktop
Lessons | Mobile
Tablet
Desktop
Staff | Mobile
Tablet
Desktop
Liveries | Mobile
Tablet
Desktop
Lifestock | Mobile
Tablet
Desktop
Navbar | Mobile
Tablet
Desktop